Minutes of the Camcore SA Technical meeting held on Tuesday 6 October 2009

1. Attendance:

Mondi: 		Kitt Payn, Marius Du Plessis

PG Bison:		Julian Moreno Chan

Sappi:			Andre Nel, Kgosi Mongwalgetsi

MTO:			Deon Malherbe

KLF:			Glen Mitchell, Nico Olivier, Bonnita Meyer, Phillip Hongwane

HM:			Botha Maree

Chikweti:		John Mudekwe

Border Timbers:	Irvine Kanyemba, Lot Chinyadza

East Africa:		Benson Kanyi, Rose Kirera

2. Minutes of previous meeting:

The minutes from the previous meeting held on the 30 May 2009 were accepted.

3. Planning the distribution of 2009/10 hybrid trials

Glen Mitchell will commence employment with York Timbers on the 12 October 2009. However, in the short term he will continue to coordinate the distribution of Camcore hybrid material produced in the Tweefontein nursery. The transport of material is to be arranged by the receiving member.

Chikweti and Border Timbers will likely receive their material before the end of 2009. Import permits and phytosanitory certificates need to be arranged beforehand. One proposal is for Chikweti to collect the material from South Africa and re-distribute the material to Border Timbers and possibly East Africa. However, the ideal planting season for East Africa may not coincide. The South African members will receive their material in 2010.

The proposed date of collection by each member is as follows:

| Member | Date |
| --- | --- |
| Chikweti and Border Timbers | November/December 2009 |
| PGB and Mondi | January/February 2010 |
| HM | February/March 2010 |
| Sappi | March/April 2010 |
| MTO and East Africa | April/May 2010 |

Blanking material will be included with the shipment of each test. An effort will be made to provide at least 8 plants per treatment for blanking. To account for the inevitable size differences between different treatments, it was suggested that each member measure the height and/or root collar diameter of each cutting before planting.

The P. patula seedlings included in the first round of hybrid trials have been found to have poor survival. This treatment will be replaced by P. patula cuttings comprising two families having demonstrated higher levels of Fusarium resistance. Any member wanting to include additional treatments of their own should inform Glen ahead of time so that he can include them in the trial design.

4. New P. patula second generation progeny trial series

Seed provided by Sappi and KLF has been distributed. KLF will provide three hybrid controls (pat x tec, pat x ooc, pat x gre), which are to be collected from the Tweefontein nursery by each member.

Are we are top of this? Do these trials have Camcore codes? Do we know the family composition?

Proposed planting date of the P. patula trial by each member is as follows:

| Member | Date |
| --- | --- |
| PGB and KLF | December 2009 |
| Mondi | March 2010 |
| Sappi and MTO | April 2010 |
| HM | October 2010 |

5. New P. greggii second generation progeny trial series

The recommended planting elevations discussed during the meeting were as follows: P. greggii (S) may be planted between 1300-1500m; whereas P. greggii (N) should be planted above 1500m.

P. greggii (N): The P. greggii (N) series, comprising up to 64 families, has been distributed by Mondi and Sappi. MTO declined their seed package and gave it to PGB. Why would MTO bow out of P. greggii? Pitch canker concerns? The trials are scheduled to be established towards the end of 2010 or the beginning of 2011.

P. greggii (S): There are not many seedlots currently available in storage. As per the minutes of the previous meeting, it was suggested that members make an effort to collect additional seed during 2009. Furthermore, a request for seedlots harvested from Camcore selections in Brazil has been made. The trials are also scheduled to be established towards the end of 2010 or the beginning of 2011.

6. Second generation seed for the non-South African Camcore members

Chikweti has sown their second generation P. maximinoi and P. tecunumanii seedlots received from Camcore. They plan to plant one trial of each species in December 2009. Additional seed collections from P. maximinoi and P. tecunumanii are to be done by KLF and Sappi, respectively. This seed will be sent to Border Timbers and East Africa towards the end of 2010.   We are breaking our two year rule on seed distribution from Camcore trials.  How are we going to make sure we can track the distribution of the trials so that they go with a Camcore code?

Similarly, additional seed collections from P. patula selections need to be done by Sappi and KLF so that second generation trails (duplication of point No. 4 above) may be established by Chikweti, Border Timbers and East Africa. Same question as above. Seedlots will be available for distribution towards the end of this year, with sowing to be done in 2010. The inclusion of seedlots from non-Camcore selections (e.g. Zimbabwean selections) in the trial series is encouraged. (How do we follow the Zimbabwean control lots in Raleigh-code numbers etc.)

7. Site/Species trial series

Most members have sufficient seedlings for the establishment of at least one trial each; the exception being Sappi who experienced frost damage. Sappi and KLF have decided not to establish trials and will donate their seedlings to HM and PGB. Gary, how does this affect site coverage? The scheduled planting of these trials is as follows: MTO plan to plant in October 2009, where as HM, PGB and Mondi plan to plant in November/December 2009.

The non-South African members have expressed interest in partaking in the site/species trials. Interested members should contact Sappi or KLF and request the relevant seedlots. Test codes?

8. Hybrid cold hardiness study

Bill has not received information (scoring sheets) regarding the cold damage assessments done this winter. Most members did not score the level of frost damage but simply measured survival at different intervals throughout the winter months. These data are to be sent to Willi Woodbridge before the end of December 2009. If possible, please include climatic data generated by an infield Hobo.

9. Cone and flower survey

A document listing the results of the cone and flower survey has been distributed by Bill Dvorak. This will likely be discussed further at the meeting in Uruguay.

10. Article on Camcore conservation parks

An article promoting the Camcore Conservation Parks has been written by Glen Mitchell and is presently being edited by Arnulf Kanzler. The article will likely be published in Wood SA, with an abridged version published in other popular literature including Farmers Weekly. Glen Mitchell will contact the editor of WOOD SA to determine whether it will be acceptable to publish an abridged version in other magazines.

11. Grafting workshop

Members continue to experience sub-optimal grafting success. A grafting workshop geared for supervisors/assistants was proposed. The multi-day workshop will be coordinated by Andre Nel and will likely take place at Sappi’s Ngodwana mill in June 2010.

Finally, we would like to thank the staff of KLF for hosting the meeting at the KLF Research Centre, Sabie.